## Dashboard
Project All-Aboard — Planning Workbook
Area | Status | Owner | Next Step | MVP Priority | Risk | Target | Notes
PRD | Complete v0.1 | Brendan | Review for scope/voice | P0 | Medium | Final v0.2 | Living product source of truth
Competitive Landscape | Drafted | Brendan | Validate with deeper source review | P0 | Medium | Decision matrix | Current row scoring is directional
Prototype | Complete clickable HTML | Brendan | Test four primary flows | P0 | Low | Demo script | Designed for review, not production
Data Graph | Defined | TBD | Create synthetic dataset | P0 | High | Seed graph | Avoid real employee data in prototype
Trust/Privacy | Defined doctrine | TBD | Convert into product rules | P0 | High | Trust policy | Critical product differentiator
Systems Impact | Conceptual | TBD | Mock impact map from sample systems | P1 | Medium | Demo flow | Core beyond-HR wedge
Integration Strategy | Defined | TBD | Prioritize M365 + HRIS + ServiceNow | P1 | High | Connector backlog | Avoid being tied to one incumbent

## Competitive Matrix
Capability | Microsoft 365/Viva/Copilot | Workday | Oracle HCM | SAP SuccessFactors | Glean | ServiceNow | LinkedIn | Polinode | All-Aboard Target
Formal org hierarchy / visual org chart | ● | ● | ● | ● | ◐ | ● | ◐ | ◐ | ●
Role-aware onboarding journeys | ◐ | ● | ● | ● | ◐ | ● | ○ | ◐ | ●
AI onboarding mentor / conversational guide | ◐ | ◐ | ◐ | ◐ | ● | ● | ○ | ○ | ●
Skills / expertise profiles | ● | ● | ● | ● | ● | ● | ● | ◐ | ●
Infer expertise from actual work | ● | ◐ | ◐ | ◐ | ● | ◐ | ● | ◐ | ●
Resume / prior-career history incorporated | ◐ | ● | ● | ◐ | ◐ | ● | ● | ○ | ●
Historical coworker / professional relationships | ◐ | ○ | ○ | ○ | ◐ | ○ | ● | ● | ●
Reference/referral relationship as evidence | ○ | ○ | ○ | ○ | ○ | ○ | ◐ | ○ | ●
Collaboration / works-with graph | ● | ○ | ○ | ○ | ● | ◐ | ● | ● | ●
Find internal SME | ● | ◐ | ● | ● | ● | ◐ | ◐ | ● | ●
Find warm introduction path | ◐ | ○ | ○ | ○ | ◐ | ○ | ● | ● | ●
Enterprise-wide knowledge search | ● | ○ | ○ | ○ | ● | ● | ○ | ○ | ●
Explain institutional history / why this way | ◐ | ○ | ○ | ○ | ● | ◐ | ○ | ○ | ●
Application / systems inventory | ◐ | ○ | ○ | ○ | ◐ | ● | ○ | ○ | ●
System dependency / integration graph | ◐ | ○ | ○ | ○ | ◐ | ● | ○ | ○ | ●
Downstream technical impact analysis | ◐ | ○ | ○ | ○ | ◐ | ● | ○ | ○ | ●
Connect affected systems to responsible people | ◐ | ○ | ○ | ○ | ◐ | ◐ | ○ | ○ | ●
Combine people + system + knowledge reasoning | ◐ | ○ | ○ | ○ | ◐ | ◐ | ○ | ○ | ●
Employee-first anti-surveillance doctrine | ◐ | ◐ | ◐ | ◐ | ◐ | ◐ | N/A | ○ | ●

## MVP Roadmap
Horizon | Workstream | Deliverable | Status | Priority | Notes
Now | Artifact set | PRD, deck, workbook, prototype | Done | P0 | These four files
Weeks 1-2 | Synthetic data model | People, systems, documents, projects, relationships | Planned | P0 | Use fake data first
Weeks 3-5 | Graph MVP | Build lightweight human/knowledge/systems graph | Planned | P0 | No live enterprise data
Weeks 6-8 | Prototype flows | Ask, Find Expert, Warm Path, Impact Analysis | Planned | P0 | Clickable prototype
Weeks 9-10 | Validation scripts | Run utility, manufacturing, software personas | Planned | P1 | Capture success/failure
Weeks 11-12 | Demo packaging | Demo deck, risks, integration plan | Planned | P1 | Decide continue/pivot

## Data Sources
Domain | Likely Source | Data Captured | Trust Type | Risk | MVP Priority | Primary Use
HRIS | Workday / Oracle / SAP | Role, manager, job family, location, start date | Authoritative | Medium | P0 | Role-aware onboarding and permissions
Identity/Access | Entra ID / Okta | Groups, entitlements, org identity | Authoritative | High | P0 | Permission filtering before retrieval
Collaboration | Teams / Outlook / Slack | Meetings, messages, channels, collaborators | Derived | High | P1 | Use only privacy-preserving signals
Knowledge | SharePoint / Confluence / Drive | Docs, SOPs, ADRs, training, policies | Source-grounded | Medium | P0 | Citations and institutional history
Work Mgmt | Jira / Azure DevOps / Smartsheet | Projects, epics, tickets, owners | Source-grounded | Medium | P1 | Actual work history
Systems | ServiceNow CMDB / APM / API catalog | Applications, integrations, owners | Authoritative | High | P1 | Impact analysis
Career/Profile | Resume / LinkedIn import | Prior employers, projects, skills, references | Employee opt-in | High | P1 | Hidden expertise and warm paths

## Risks
Risk | Impact | Likelihood | Mitigation | Status | Priority
Employee surveillance perception | High | High | Explicit employee-agency doctrine; no individual scoring; opt-in external history | Open | P0
Permission leakage | High | High | Pre-retrieval access filtering; source-level ACLs; audit trail | Open | P0
Stale/conflicting data | High | Medium | Source ranking, last-verified dates, conflict warnings | Open | P0
Microsoft/Glean/ServiceNow adjacency | Medium | High | Position as orchestration across systems, not one-source feature clone | Open | P1
Patent/prior-art constraints | Medium | Medium | Avoid claiming novelty on expert graph primitives; focus on product orchestration | Open | P1
Integration complexity | High | Medium | Start synthetic; then one HRIS + one knowledge + one systems connector | Open | P1
Hallucinated institutional knowledge | High | High | Citations, confidence, and refusal when source support is weak | Open | P0

## Feature Backlog
ID | Feature | User Story / Acceptance | Priority | Release | Domain | Notes
ASK-001 | Ask organizational question | Employee can ask 'Why is this system this way?' and receive cited answer | P0 | MVP | Knowledge Graph
EXP-001 | Find expert | Employee can find SME based on work history and documents | P0 | MVP | Human Graph
PATH-001 | Warm introduction path | System suggests reasonable introduction path with minimal relationship exposure | P0 | MVP | Human Graph
IMPACT-001 | Impact analysis | System maps downstream systems, teams, and docs for proposed change | P0 | MVP | Change/System Graph
LEARN-001 | 30/60/90 plan | Role-aware onboarding plan adapts to assigned projects | P1 | MVP+ | Learning
CAP-001 | SME knowledge capture | Interview retiring/transitioning SME and convert to governed knowledge | P1 | MVP+ | Knowledge Capture
TRUST-001 | Trust controls | Visibility settings for resume/history/reference data | P0 | MVP | Trust
ADMIN-001 | Source quality admin | Admin can rank authoritative sources and flag stale/conflicting content | P1 | MVP+ | Governance

## Scenarios
Scenario | Prompt | Expected All-Aboard Response
New utility PM | I need to understand why outage-map changes need four teams | Answer explains OMS/GIS/IAM/Web dependencies and owners with citations
HP-style campus employee | I need someone who understands device telemetry privacy | Find expert + internal collaborator + warm introduction path
Internal transfer | I moved from hardware to cloud platform team | Generate re-onboarding plan and 8 people to meet
Change request | We want to replace a vendor API | Impact map lists systems, teams, policies, and historical decisions
Succession | A 30-year SME is retiring | Capture interview and convert undocumented knowledge to reviewed artifacts

## Sources
Source | URL
Microsoft Viva Org Explorer | https://learn.microsoft.com/en-us/viva/people-in-viva/introducing-org-explorer
Microsoft Viva organizational data / People Skills | https://learn.microsoft.com/en-us/viva/organizational-data
Microsoft Viva Insights network collaboration insights | https://learn.microsoft.com/en-us/viva/insights/advanced/analyst/network-collaboration-insights
Glean knowledge graph | https://docs.glean.com/security/knowledge-graph
Glean expert search | https://docs.glean.com/agents/actions/glean/expert-search
ServiceNow Application Portfolio Management | https://www.servicenow.com/products/application-portfolio-management.html
ServiceNow Employee Center | https://www.servicenow.com/products/employee-center.html
Workday Skills Cloud | https://www.workday.com/en-us/pages/cb/workday-skills-cloud.html
Oracle Dynamic Skills | https://docs.oracle.com/en/cloud/saas/talent-management/faudy/components-of-dynamic-skills.html
SAP Talent Intelligence Hub | https://help.sap.com/docs/successfactors-platform/using-talent-intelligence-hub/talent-intelligence-hub
LinkedIn Economic Graph | https://engineering.linkedin.com/teams/data/data-infrastructure/graph
Polinode organizational network analysis | https://www.polinode.com/info/organizational-network-analysis